## Gantt Chart
GANTT CHART Surrounded by Crime
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | EFFORT | SPRINT 1 | [9 empty] | SPRINT 2 | [9 empty] | SPRINT 3 | [7 empty] | SPRINT 4
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  | WEEK 10 |  |  |  |  | WEEK 11
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | M | T | W | R | F | M | T | W | R | F
1 | SPRINT 1
1.1 | Building project structure | Aaron C | 2024-09-25 | 2024-10-09 | 4 | bar: WEEK 1 F to WEEK 2 T; WEEK 8 M to WEEK 8 T
1.2 | Styling web pages | Emil K | 2024-09-25 | 2024-10-09 | 6 | bar: WEEK 2 W; WEEK 8 M to WEEK 8 T
1.3 | Setting up the backend for any database integration | Scott S | 2024-09-25 | 2024-10-09 | 5 | bar: WEEK 2 W to WEEK 2 F; WEEK 8 M to WEEK 8 T
2 | SPRINT 2
2.1 | Creating a new account | Aaron C | 2024-10-09 | 2024-10-23 | 3 | bar: WEEK 4 M to WEEK 4 R; WEEK 5 M to WEEK 5 W
2.2 | Making a new report | Emil K | 2024-10-09 | 2024-10-23 | 5 | bar: WEEK 4 F to WEEK 5 F
3 | SPRINT 3
3.1 | Sorting reports | Scott S | 2024-10-23 | 2024-11-06 | 8 | bar: WEEK 5 M to WEEK 5 W; WEEK 7 M to WEEK 8 W
3.2 | Testing and Debugging | Emil K | 2024-10-23 | 2024-11-06 | 6 | bar: WEEK 5 M to WEEK 5 W; WEEK 7 M to WEEK 8 W
4 | SPRINT 4
4.1 | Api for getting crimes from other sources | Scott S | 2024-11-06 | 2024-11-20 | 7 | bar: WEEK 5 M to WEEK 5 W; WEEK 8 M to WEEK 8 T; WEEK 10 M to WEEK 11 T
4.2 | Pictures/Videos for reports | Aaron C | 2024-11-06 | 2024-11-20 | 5 | bar: WEEK 5 M to WEEK 5 W; WEEK 8 M to WEEK 8 T